Smarty

Feature Breakdown Document

AI-Powered ICP Smart Contract Auditor · v1.0

Each big feature is broken into atomic, implementable tasks. Tasks are sequenced in dependency order. Estimated effort is relative: S = <2hrs, M = 2–4hrs, L = 4–8hrs.

# Feature 1: ICP Project Scaffolding

| Task | Description | Effort |
| --- | --- | --- |
| 1.1 Create dfx.json | Define smarty_backend (motoko) + smarty_frontend (assets) canisters | S |
| 1.2 Create main.mo skeleton | Actor with health(), stub auditContract(), stub getLastAudit() | S |
| 1.3 Wire assets canister | Point to dist/, add dependency on backend, test dfx deploy locally | S |
| 1.4 Vite proxy config | Add /api proxy to 127.0.0.1:4943 in vite.config.ts | S |
| 1.5 dfx generate declarations | Run dfx generate smarty_backend, commit declarations to src/ | S |

# Feature 2: Backend Canister — Audit Logic

| Task | Description | Effort |
| --- | --- | --- |
| 2.1 Define Motoko types | AuditResult and Issue types in types.mo | S |
| 2.2 Stable storage | var lastAudit : ?AuditResult in stable memory with preupgrade/postupgrade | M |
| 2.3 Build Claude prompt | Function to construct system + user prompt from code + language | M |
| 2.4 HTTPS outcall to Claude | ic_cdk http_request to Anthropic API, parse JSON response | L |
| 2.5 Response transformer | Strip non-deterministic headers for ICP consensus | S |
| 2.6 auditContract() method | Wire prompt builder + outcall + store result in stable var | M |
| 2.7 getSupportedVulns() | Return static list of vulnerability classes as query | S |
| 2.8 Error handling | Return Result<AuditResult, Text> with meaningful error messages | M |

# Feature 3: Frontend — Code Input

| Task | Description | Effort |
| --- | --- | --- |
| 3.1 CodeEditor component | Textarea with monospace font, line count display, placeholder text | S |
| 3.2 Language toggle | Motoko / Rust pill toggle, persists to localStorage | S |
| 3.3 File upload | FileReader reads .mo/.rs into textarea, validates extension | M |
| 3.4 Audit button | Disabled when empty, spinner on loading, calls canister actor | M |
| 3.5 Error toast | Show user-friendly error if canister call fails | S |

# Feature 4: Frontend — Results Display

| Task | Description | Effort |
| --- | --- | --- |
| 4.1 RiskGauge component | Circular SVG gauge, color-coded by score range | M |
| 4.2 IssueCard component | Severity badge, title, description, expandable fix section | M |
| 4.3 Filter tabs | All / Critical / High / Medium / Low / Info pills that filter issue list | S |
| 4.4 Fix snippet display | Before/after code blocks with syntax tint, Copy button | M |
| 4.5 Clean checks section | Green checkmarks for passed vulnerability checks | S |
| 4.6 Save to history action | Serialise AuditResult to localStorage with timestamp + filename | S |

# Feature 5: Audit History

| Task | Description | Effort |
| --- | --- | --- |
| 5.1 HistoryList component | Read localStorage, render sorted list of past audits | S |
| 5.2 HistoryRow component | Score chip, filename, language, issue count, relative time, View button | S |
| 5.3 View past audit | Re-render Results page from stored AuditResult (no re-audit) | M |
| 5.4 Clear history | Clear all localStorage entries with confirmation modal | S |
| 5.5 Empty state | Friendly prompt to audit first contract when history is empty | S |

# Feature 6: About Page + Docs

| Task | Description | Effort |
| --- | --- | --- |
| 6.1 About page content | Vulnerability classes list, privacy note, supported chains | S |
| 6.2 README Local ICP section | dfx commands, prereqs, troubleshooting — from finalized MVP prompt | S |
| 6.3 Inline code blocks | Style code blocks in About page with JetBrains Mono | S |

# Implementation Order (Dependency Sequence)

- Feature 1 (Scaffolding) — must be first, unblocks everything.

- Feature 2 (Backend canister) — can develop in parallel with Feature 3.

- Feature 3 (Code input UI) — unblocks Feature 4.

- Feature 4 (Results display) — requires Feature 2 + 3 complete.

- Feature 5 (History) — requires Feature 4 saving results.

- Feature 6 (Docs + About) — last, written from real implementation.

# Total Effort Estimate (v1 MVP)

| Feature 1 — Scaffolding | ~2 hrs |
| --- | --- |
| Feature 2 — Backend canister | ~10 hrs |
| Feature 3 — Code input | ~4 hrs |
| Feature 4 — Results display | ~6 hrs |
| Feature 5 — History | ~3 hrs |
| Feature 6 — Docs | ~1 hr |
| Total | ~26 hrs (solo dev, focused sessions) |